Protection Ordinateur AS — 5-Step MSP + App Launch Brief

Updated: February 26, 2026

This working brief packages the discovery, onboarding, security, and launch playbooks we execute for Québec SMEs so owners, product leads, and compliance officers stay aligned from kickoff through MSP care.

1. Engagement Snapshot

• Business outcomes: stabilize IT + Microsoft 365, launch bilingual customer apps, and earn Law 25/SOC 2 readiness without stalling GTM.

• Guardrails: maintain ≥99.5% uptime during cutovers, keep regulated data in Canadian regions, and schedule QBRs before close-out.

• Success indicators: signed Sprint 0 backlog, first release submitted to Apple & Google with ≥4.8 beta rating, SOC 2 readiness score ≥80%, onboarding checklist 100% complete with evidence.

2. Stakeholders & Governance

• Executive sponsor (client CEO/owner): approves scope, risk, and escalations — joins monthly exec syncs.

• Product owner: prioritizes backlog, signs UX copy, drives GTM — weekly sprint review + shared Kanban.

• POAS vCIO (Andrei Suba): owns MSP onboarding, SOC 2 tracker, stakeholder reporting — weekly status + QBR chair.

• Delivery lead (POAS product studio PM): runs sprints, dependencies, and vendor coordination — daily async standups.

• Security & privacy officers: maintain controls, breach comms, and evidence room — bi-weekly risk huddle.

3. Five-Step Playbook with Outputs

1) Audit & alignment (week 1): interviews, asset map, Law 25/PIPEDA review → readiness scorecard + prioritized gap list.

2) Secure foundations (weeks 2-3): NinjaOne & Intune baselines, identity hardening, credential vault → configuration pack + security baseline evidence.

3) Product sprints (weeks 4-9): two-week rhythm bundling UX, design, bilingual QA, CI/CD → design system, demos, release notes.

4) Launch & transition (weeks 10-12): app-store submissions, comms, observability dashboards → cutover plan, training deck, 30-day on-call roster.

5) Autonomous operations (day 31+): 24/7 NOC/SOC, automation backlog, retros → QBR pack, health KPIs, optimization roadmap.

4. MSP Onboarding Checklist

• Discovery & scope: client provides org chart, app inventory, contracts; POAS validates scope & seeds Trello/ClickUp onboarding board.

• Access & accounts: executive approval for credential transfer, MFA roster; POAS secures vault + enforces MFA.

• Tool rollout: endpoint list + sites; POAS deploys NinjaOne agents, PSA integration, backup jobs.

• Security baseline: data classification, regulatory inputs; POAS runs restore tests, vulnerability scans, incident-response workshop.

• Go-live & cadence: confirm QBR attendees + channels; POAS issues escalation paths, end-user welcome kit, QBR schedule.

5. What is a SOC and a Readiness Tracker?

• SOC (Security Operations Center) = the people, tooling, and 24/7 monitoring muscle that watch over your Microsoft 365, endpoints, and cloud workloads. Our Montréal-based SOC combines NinjaOne telemetry, Intune, and Microsoft Sentinel alerts so threats are contained before they touch your backups or customer data.

• Readiness Tracker = the lightweight dashboard that shows exactly where you are on the SOC 2/Law 25 journey. We outline the 90-day loop (gap analysis → policies → controls → evidence → mock audit) and document Responsible/Accountable owners. You see what’s done, what’s blocked, and which artifacts an auditor will request so surprises disappear.

6. SOC 2 Readiness Timeline (90 days)

• Days 1-14 — Gap analysis: scope TSCs, evaluate CC1-CC9, publish remediation plan (POAS compliance lead Responsible, client security owner Accountable).

• Days 15-30 — Policy drafting: finalize ~20 core policies, vendor inventory, incident response updates (POAS compliance Responsible, client HR/Ops Consulted).

• Days 31-60 — Control implementation: enforce access control, monitoring, change mgmt workflow (POAS engineering Responsible, client IT Accountable).

• Days 61-75 — Evidence & monitoring: collect logs, access reviews, awareness training proofs (shared ownership).

• Days 76-90 — Mock audit & freeze: run mock auditor review, finalize system description, freeze evidence room.

7. Communication & Governance Rhythm

• Weekly delivery sync — backlog, blockers, KPI snapshot → Kanban export + risk log.

• Bi-weekly risk/compliance huddle — control status, incidents, vendor review → SOC 2 tracker update.

• Monthly executive update — financials, outcomes, decision requests → 1-page exec brief.

• Quarterly business review — scorecard, roadmap, automation backlog → QBR deck + action tracker.

8. Kickoff Agenda (Why it matters)

A tight 90-minute session sets tone and responsibilities. Topics:

1) Welcome & objectives — align expectations and confirm decision-makers.

2) Business context & success criteria — hear revenue goals, customer mandates, compliance must-haves.

3) Scope & guardrails — agree on what we are/are not doing so budgets don’t creep.

4) Timeline & milestones — review the 12-week plan, MSP handoff, and blackout dates.

5) Roles/RACI & escalation paths — name every owner so blockers have a route.

6) Tooling & comms plan — confirm Teams/Slack channels, documentation, dashboards.

7) Risk & assumption review — capture what keeps leadership awake today.

8) Decisions + action items — assign next steps so momentum starts immediately.

9. Delivery Timeline & Metrics

• Discovery + foundations ≈ 6 weeks · Builds 6–10 weeks · Transition 30 days · MSP care ongoing.

• KPI targets: 63% faster incident response, 4.9★ mobile launches, 98.7% SLA adherence, customer satisfaction ≥ 4.7/5.

10. Immediate Next Steps & Contacts

• Confirm kickoff attendees/date (within 5 business days).

• Share onboarding board + evidence request list with stakeholders.

• Provide vendor/security questionnaires for SOC 2 Phase 1.

• Schedule first QBR now to set cadence expectations.

Contact: support@ProtectionOrdinateurAS.com · 514-970-5667 · Teams/Slack channel issued at kickoff.